## Sheet1
Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Project setup, ideation & design docs (repo, environment, objectives, skill tree)
Literature review & Chapter 1–2 drafts
MILESTONE: Project Plan report submission
Prototype v0: frontend, MCQ flow, level navigation
Question bank (30+ questions in JSON)
Answer checking (numerical + symbolic)
Gamification layer (XP, streaks, hearts, badges)
AI hints + adaptive difficulty integration
Alpha testing & fixes
MILESTONE: Semester 1 progress presentation
Deployment prep (NotebookLM, AI Studio) + GEAP deployment
Evaluation design (pre/post tests, survey, consent)
Recruitment & pilot test
User study & data collection
Data analysis (engagement + learning outcomes)
Final report writing (Ch 3–6) + poster
MILESTONE: Final submission, GAI declaration & presentation